## Sheet1
Objective | Milestone / Deliverable | Actions Be detailed; Point form is acceptable | Timeline | Resources Include specifics, such as type of services, RAM, CPU etc. | Person(s) Responsible
What are the key objectives for the project? These are the things, that once achieved, indicate the project was successful. | Break the objectives into one or more deliverables – this could be documentation, tests, other plans etc. Insert one (1) milestone per row. | Break the deliverables into actions that must be completed to achieve the deliverable. Insert one action per row. | For each of the actions you have defined, indicate the timelines involved – such as the session, a date or time, a duration or a sequence. | For each of the actions identify the relevant resources. Think people, spaces, time, costs, equipment and materials. | For each of the actions identify the people who will be responsible for undertaking the action and reporting the outcomes.
1 LAN network – win, svr, ubuntu, kali for setup and later implementation – permissions, details, access for AD | 1. Build active directory, structured hierarchy, shared files/folders access, group policy | 1. Configure Domain controller 2. Create Administrator & User accounts 3. Create shared folders 4. Set up Group Policy permissions | 1 week | Do resources like people and spaces refer to resources required on our end or on the clients end? Does time in this column differ from the timline column? 1. Domain controller device 2. Secure Server room 3. Network Admin | FYT Network engineer Clients in-house domain administrator
| 2. Deploy 10 Client devices and Server device | 1. Procure hardware 2. Create windows images 3. Install Windows Server 4. Install images on clients 5. Add devices to domain | 3-4 weeks for laptop & Server procurement 5 Days for imaging, installation & initial config | 1. Laptops & Accessories - $3350 ea - $33500 for all 10 (Dock, Wireless mouse & Keyboard, laptop bag, 1x monitor) Laptop specs (ThinkPad X1 Carbon Gen 11): - Intel i7 1355U - 16 GB LPDDR5 6400MHz memory - 512 GB M.2 SSD - WiFi 6E & Bluetooth 5.1 wireless card 2. VMware ESXI Server: Dell PowerEdge R760xs - $28 448 - 2x Xeon Gold 6426Y 16 core - 12 x 32GB RDIMM - 12x 2.4 Tb SAS ISE HDD - Dual, Hot-plug, Power Supply Fully Redundant (1+1), 1400W Windows server 2022 Standard 16 Core license w/ 10 CAL - $2653 Estimated budget cost: $2500 for Windows server Standard, hardware cost: $25k, price may change dependant on market. Assembly Labour: $150. Window server: $25k per machine. Windows Laptops: $3k-3.5k per machine | FYT Network engineer Clients in-house domain administrator
| 3. Proxy server and firewall | 1. Procure Proxy Device 2. install CC Proxy 3. Procure Firewall Device 4. Configure ZPF in the interim | 2-4 Weeks to procure devices 3 days for ZPF configuration | Australian Seller of Netgate 1537 - AUD$3747 Snort IDS/IP - Free Snort Subscriber Ruleset Subscription - USD$399/Sensor (~AUD$630 at time of writing) | FYT Network engineer Clients in-house domain administrator
| 4. Kali – pen test | 1. Install Kali image 2. Connect kali machine to the network | 3 Days | Kali Linux Computer: RAM: 2GB, SSD: 50 GB, Processor: 32-single core or 64-bit CPU running at 2 GHz or Higher. Bootable CD-DVD drive/USB Stick. | FYT Network engineer FYT Red Team
| 5. Ubuntu Server – Virtualised SIEM tool | 1. Install Ubuntu Server VM on Server 2. Configure ELK 3. Configure Logging pipelines from Windows Server | 2 Weeks to deploy, test and monitor | Ubuntu Server ELK Stack - Elastic - Logstash - Kibana | FYT Blue Team
2 Create Web Service (Microsoft Azure) | 1. Establish Cloud service as an extention to faciliating web services | Create Microsoft Azure account - Install Virtual Machine to establish webpage - implement security protocols for users | Approx. 3-5 days | 1. Microsoft Azure Account & subscription 2. Azure VM Images (Windows Server) 3. Virtual machines = Premium SSD; Encryption at rest with platform managed key; Virtual network; Default subnet IP | Cloud Engineer - build, implement, and maintain cloud service
| 2. Create backup | - Create Azure File Share (system to mount files to cloud platform) - Create Recovery Services Vault (interface for storing & managing recovery points, and perform back-up) - Create policy (schedule, duration & timing, access control) - Configure backup settings (file type, applicable policies | Approx. 3-7 days | 1. Azure Storage (100 GB; $69 AUD/month; pay-as-you-go subscription) 2. Azure File Share 3. Recovery Services Vault | Cloud Engineer - build, implement, and maintain cloud service IT Administrator - manage & update policies; set frequency and type of backup; monitor & report backup system
3 Install pfsense w/ VPN to Azure and implement a SIEM tool | 1. Build Ubuntu with pfsense/Snort IPS and SIEM tool | 1. Install and set up pfsense firewall 2. Setup pfsense connection on the Ubuntu device 3. Add snort to pfsense 4. Reroute the AD server's DNS through to the firewall 5. Configure pfsense to filter traffic and send alerts | Order firewall: 3 weeks Setup: 1 day Monitor & optimise: 2 weeks | Setup firewall: 1. Firewall software 2. Dedicated hardware firewall device 3. SIEM tool subscription | Cyber security/networking technicians and IT staff
| 2. Setup site-to-site VPN for cloud use | 1. Create VPN between the cloud and LAN 2. Setup VPN to only be available when pfsense is active | Setup: 1 day Monitor & optimise: 1 week | 1. Configure both the on-site and cloud "routers"for the VPN encryption tunnel 2. Test the VPN tunnel | Cloud and networking technician
| 3. Create replica domain controller | 1. Create an Azure Windows Server VM 2. On the VM, create and add a domain controller to existing domain 3. Add the AD directory services and DNS role corresponding to the on-site domain | Setup: 1 day Monitor & optimise: 1 week | 1. Azure account (again) 2. Azure Windows Server VM, specs, $$ | Cloud technician and system admin
| 4. Create 10 Windows 10 VM for employees with antivirus installed | 1. Create a Windows 10 VM on Azure 2. Install antivirus software and any other necessary applications for work/security 3. Connect the VM to the RDC 4. Create an image and generate duplicate VM | Setup: 1 day Monitor & optimise: 3 days | 1. Azure Windows 10 VM x 10, specs, $$ | Cloud technician and IT staff
| 5. Setup IPS to check data during sync | 1. Port forward traffic from Azure through the IPS | Setup: 1 day Monitor & optimise: 3 days | 1. IPS, extra capacity? specs, $$ | Cyber security/networking technicians and IT staff
4 Wireless network | 1. Segmenting the wireless router away from the LAN network | 1. Segmenting the network using VLAN with a switch 2. Configure the router to have subinterfaces 3. Implement ACL to control the flow of network traffic 4. Test all port forwarding and connections are working | Setup: 1 day Monitor & optimise: 3 days | Router | Cyber security/network engineers
| 2. Proxy server for authentication, separate from LAN | 1. Downloading CC proxy onto the server for wireless connections 2. Create a security group for vairous permissions (e.g Blocking nsfw from workers) 3. Add users to those security groups 4. Create the permissions on CC proxy and add the security group to them | Setup: 1 day Monitor & optimise: 3 days | Windows Server machine | Cyber security/network engineers
| 3. Enabling wireless connections | 1. Activate the wireless network. 2. Setup WPA2 passwords, disable SSID broadcast 3. Get wireless devices connected to the network | Setup: 1 day Monitor & optimise: 5 days | Wireless routers Wireless machines | Cyber security/network engineers
| 4. Applying web filters, active hours/off-hours, MAC filtering and regular updates. | 1. Configure web filters 2. Assign active and off-hours for connectivity 3. Apply mac filtering of devices 4. Update firmware/software on wireless machine. | Setup: 1 day Monitor & optimise: On-going | Wireless Routers, Wireless Devices, Wireless Machines | Cyber security/network engineers/network technician