## Vuln 1 - Josiah
Vulnerability: Employees are not trained to identify phishing emails and the proxy is not set up to block these sites
Actions | Strategies | Timeline | Resources | Person(s) Responsible
Download CCproxy | Download CCproxy from the browser and install it to the Windows Server | 1.5 hours | Windows Server CCproxy (Free) | Fix Ur Things Tech staff
Configure security group | Create a single security group naming it "Block Phishing" add all users to it
Configure CCproxy | Create a user on CCproxy naming "Phishing Proxy" Block cloudflare Add the security group to CCproxy Give it the Phishing Proxy profile
Create Emails | Create several emails that attempt to imitate the name of the business Use numbers or similar looking letters to resemble the name | Sending out emails should be done weekly Training is a constant ongoing process |  | IT Staff
Prepare Emails | Prepare messages for the email that lead the reciever to click on the link focus on urgency to get them to click as quickly as possible e.g PASSWORD RESET URGENT |  | Outlook emails Kali Linux
Send out emails | Send out the emails to all company workers List off those who clicked on the link for training

## Vuln 2 - Will
Vulnerability: No IDS/IPS to detect and respond to suspicious traffic
Actions | Strategies | Timeline | Person(s) Responsible | Resources
Install & Configure Snort on the Firewall | Install from PFsense package manage manager Configure interfaces Train client staff on configuration | 0.5 Day | 1x Fix Your Things tech 1x Client Staff | Firewall:
Create custom rule to detect Syn Floods | Monitor all Destination ports Monitor Syn Packets Trigger when 60 packets from the same source are identified within 20 seconds genereate Alert and Automatically block source | 1 day | 1x Fix Your Things tech | o NETGATE 1537 Security Gateway - $3747 o PFsense + & TAC LITE included with Netgate device o Snort IDS/IPS - USD$399/Yr (~AUD$630 at time of writing)
Enable Arpspoof Preprocessor in snort to detect ARP Spoofing | Enable Preprocessor specify list of static hosts IP addresses and MAC addresses configure alerts and blocks when detected |  | 1x Fix Your Things tech | 1 x Fix your Things tech 1x Client Staff
Enable and configure Snort subscriber and community rule sets | Initiate Subscription enable subscriber rules Add subscriber details to enable instant updates of the rule set |  | 1x Fix Your Things tech
Perform Syn Flood, Arp Spoof & Port scan tests | Execute SYN flood against sever, Firewall and other network infrastructure using ettercap Execute Arp poisoning attack using Ettercap Scan network infrastructure devices using Nmap Demonstrate alerts and blocks as continued training with client staff | 1 Day | 1x Fix Your Things tech 1x Client Staff
Monitor regular traffic to identify any false positives | Monitor alerts regularly Train Client staff to monitor alerts identify any false positive and rectify | 5 Days | 1x Fix Your Things tech 1x Client Staff

## Vuln 3 - Jimmy
Vulnerability: Wi-Fi is insecure
Actions | Strategies | Timeline | Person(s) Responsible | Required Resources
Connect to the wireless router
Configure Wireless Network | Configure the wireless router | 1 day | 1x Fix your things Tech
| Update default settings |  | 1x Client staff
| Train client sfaff on configuration |  |  |  | Wireless Router
| Install WLC device |  |  |  | IPS
| Configure WLC settings |  |  |  | Technician
Install WLC and configure WPA2 Enterprise WLAN on it | Configure VLAN interface | 1 Week | 1x Fix your things Tech |  | Educator
| Configure WLAN interface |  | 1x Client staff |  | Windows or Linux Machine
| Train client sfaff on configuration |  |  |  | Employee's time (For lessons)
Prevent Rogue AP's | Configure WLC with Rogue AP Policies
Active monitor of radio spectrum for unauthroized APs
| Train client staff on configurations and monitoring |  | 1x Fix your things Tech
| Train staff to identify legitimate devices within WLAN |  | 2x Client Staff
Prevent MiTM Attacks | Authenticate users
Monitor network for abnormal devices and traffic
| Educate staff to train employees on Wi-Fi threats. | 3 days | 1x Fix your things Tech |  |  | Webmail Service
| Educate staff to train employees on using VPNS. |  | 2x Client Staff |  |  | Time
Teach and train staff about Wi-Fi Vulnerabilities | Educate staff and apply a dedicated work device policy |  | All Employee's |  |  | Inventory Management Systems
| Educate staff to inventory BYOD to reduce cyber-risks |  |  |  |  | VPN (Self created or Third-party)
| Connect nanny IOT to newly configured wi-fi |  | 1x Fix your things Tech |  |  | Nanny CAM IOT
Arlo-nanny cam IoT configuration | Access nanny cam and configure setting from within wifi | 1 day | Company Heads |  |  | Wireless Router
| Update firmware +settings + administrative access |  |  |  |  | Technician
| Provide client staff configurations settings of the CAM |  |  |  |  | Company Heads
Client Brief
[7 empty] | Suggestion to client: | Staff access the workplace network to run their personal devices included smart phones, tablets and laptops (as needed).
[7 empty] | Use of WLC/Wireless Lan Controllers | The staff currently use their own networks when offsite. This includes tethering to a mobile phone, using free Wi-Fi hotspots and accessing home networks.
[7 empty] | for staff to connect and authenticate | Self comments :
Make it simple? Enable SSID cloaking and MAC address filtering?

## Vuln 4 - Kim
Vulnerability: Website Files are only backed up to a physical external hard drive
Actions | Strategies | Timeline | Resources | Person(s) Responsible
Set up Microsoft Azure Account (this will serve as the primary storage location for website files backup) [1.] Create storage account on Azure portal [2.] Configure the storage account (Name, Region for data residency, Performance tier e.g. Standard/Premium | [1.] Create and set up an Azure Storage Account and configure its security settings | 1 Day | People: IT staff / Cloud Engineer Space: Azure File Storage (100 GB) Cost: $69 AUD / month (pay-as-you-go subscription) | Cloud Engineer (to create and manage cloud infrastructure)
Set up Backup configuration using Azure Backup to regularly backup files. [1.] Select Azure Backup service for backups [2.] Define frequency of backup (e.g. daily, weekly), how long backups should be retained (e.g. 30 days, 90 days), and which resource should be backed up [3.] Create & configure a Backup Vault (e.g. backup policy, retention setting) | [2.] Configure backup policies and automation processes for website files | 3-5 Days |  | IT Staff/ Administrator (access control; encryption; monitor file backup & manage recovery points)
Automate the backup process through Azure Functions [1.] Create triggers for scheduled backups (e.g. daily at midnight) or event-based backups triggered by changes in website files | [3.] Develop Azure Functions to automate backup | 2-4 Days
Enable data encryption at rest and in transit to ensure the security of backup data [1.] Configure encryption during Storage Account creation using appropriate encryption option (e.g. SSE with storage service encryption) [2.] Ensure data transmitted between the virtual server and Azure Storage is encrypted | [4.] Enable encryption & access controls | 2-4 Days
Provide appropriate access to personnel in backup process and procedures | [5.] Train Administrators on Azure Backup management | 3-7 Days

## Vuln 5 - Victor
Vulnerability: Shared staff logins and accounts, with login details being recorded manually in a spreadsheet.
Actions | Strategies | Timeline | Resources | Person(s) Responsible
1. Configure domain controller | 1. Assign static IP address | 30 min total | Windows Server | IT specialist (fix ur things) and IT staff
| 2. Enable active directory services |  |  | IT specialist (fix ur things) and IT staff
| 3. Promote machine to DC |  |  | IT specialist (fix ur things) and IT staff
2. Add users and administrator accounts |  | 30 min for all 20 users |  | HR, IT specialist (fix ur things) and IT staff
3. Assign appropriate group policy permissions to user accounts corresponding to people's needs |  |  |  | Management, IT specialist (fix ur things) and IT staff
4. Add devices to the domain controller | 1. Add company devices to the AD domain | 3 hours for the 20 dedicated devices of users | All Windows 10 LAN client and Server | Management, employees, IT specialist (fix ur things) and IT staff
5. Optimise/monitor AD |  | 1 week | All Windows 10 LAN client and Server | Employees, IT specialist (fix ur things) and IT staff
6. Implement password and multi-factor authentication policy | 1. Add to company security policy | 6 hours - 1 day | Legal team | Legal contractor, cyber specialist (fix ur things)
| 2. Inform and educate employees | 1 hour sessions for all staff | Management and cyber educator | Cyber specialist (fix ur things), management
| 3. Arrange an application for MFA after Azure RDC is implemented. https://learn.microsoft.com/en-us/windows-server/identity/ad-fs/operations/configure-ad-fs-and-azure-mfa?source=recommendations | 1 hour setup, 30 min per user | AD interacting with a mobile authenticator app (Microsoft Authenticator) on employee's phones | Cyber specialist (fix ur things), management
7. (Optional) AD integration with external applications for individualised accounts